## SCHEDULE
SCHEDULE FOR BOND PROJECTS |  |  |  |  | Sponsored by: | Your Organization
| DESIGN RFP | CONTRACTS | BUDGET | CONSTRUCTION RFP | CONTRACTS | CONSTRUCTION START
TASK | DATE | DATE2 | DATE3 | DATE5 | DATE6 | DATE7
HS HVAC/SYSTEMS BALANCE | 2022-01-15 | 2022-03-15 | 2022-03-20 | 2022-04-01 | 2022-05-20 | TBD
HS CLOCK/INTERCOM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
ANNEX CLOCK/INTERCOM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
LIBRARY CLOCK/ INTERCOM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
HS SHOP CLOCK/INTERCOM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
HS FIRE SYSTEM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
LIBRARY FIRE SYSTEM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
HS SHOP FIRE SYSTEM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
ANNEX FIRE SYSTEM | 2022-01-30 | 2022-03-30 | 2022-04-15 | 2022-05-01 | 2022-05-15 | TBD
HS SHOP EXHAUST SYSTEM | 2022-02-15 | 2022-04-01 | 2022-05-01 | 2022-05-15 | 2022-05-30 | TBD
ADA RESTROOMS | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG
HS WINDOWS | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG
LIBRARY WINDOWS | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG
ELEMENTARY WINDOWS | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG | TBD AFTER SRG